## ProjectInformation
Project Name: | A Masters Student's Thesis Study
Control Time: | 4

## ProjectDefinition
Work Package | P(Risk 1) | P(Risk 2) | \No Risk\ Most Probable PV | \No Risk\ Optimistic PV (%95) | \No Risk\ Pessimistic PV (%5) | \Risk 1\ Most Probable PV | \Risk 1\ Optimistic PV (%95) | \Risk 1\ Pessimistic PV (%5) | \Risk 2\ Most Probable PV | \Risk 2\ Optimistic PV (%95) | \Risk 2\ Pessimistic PV (%5) | \Risk 1 and 2\ Most Probable PV | \Risk 1 and 2\ Optimistic PV (%95) | \Risk 1 and 2\ Pessimistic PV (%5)
LiteratureReview | 0.8 | 0 | 225 | 195 | 255 | 260 | 230 | 290
Modelling | 0.8 | 0.3 | 150 | 120 | 180 | 170 | 140 | 200 | 160 | 130 | 190 | 200 | 170 | 230
Experiments | 0.8 | 0.4 | 180 | 150 | 210 | 200 | 170 | 230 | 190 | 160 | 220 | 220 | 190 | 250
Analysis | 0.8 | 0.3 | 80 | 50 | 110 | 100 | 70 | 130 | 90 | 60 | 120 | 120 | 90 | 150

## ProjectProgress
Work Package | Expected Completion % | Completion Lower Limit | Completion Upper Limit | Actual Cost
LiteratureReview | 80 | 60 | 90 | 230
Modelling | 70 | 50 | 80 | 100
Experiments | 40 | 30 | 50 | 35
Analysis | 30 | 10 | 40 | 30

## ProjectSchedule
Work Package | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
LiteratureReview | 0.3 | 0.4 | 0.3 | 0 | 0 | 0
Modelling | 0 | 0.2 | 0.3 | 0.5 | 0 | 0
Experiments | 0 | 0 | 0 | 0.9 | 0.1 | 0
Analysis | 0 | 0 | 0 | 0.1 | 0.4 | 0.5