## ProjectInformation
Project Name: | Biofuel Refinery Construction
Control Time: | 4

## ProjectDefinition
Work Package | P(Risk 1) | P(Risk 2) | \No Risk\ Most Probable PV | \No Risk\ Optimistic PV (%95) | \No Risk\ Pessimistic PV (%5) | \Risk 1\ Most Probable PV | \Risk 1\ Optimistic PV (%95) | \Risk 1\ Pessimistic PV (%5) | \Risk 2\ Most Probable PV | \Risk 2\ Optimistic PV (%95) | \Risk 2\ Pessimistic PV (%5) | \Risk 1 and 2\ Most Probable PV | \Risk 1 and 2\ Optimistic PV (%95) | \Risk 1 and 2\ Pessimistic PV (%5)
Tanks-Preparation | 0.27 | 0 | 55000 | 52000 | 58000 | 60000 | 57000 | 63000
Skids-Preparation | 0.25 | 0.24 | 9000 | 6000 | 12000 | 10000 | 7000 | 13000 | 11000 | 8000 | 14000 | 12000 | 9000 | 15000
Civil-Preparation | 0 | 0 | 38000 | 35000 | 41000
Automation-Preparation | 0 | 0 | 50000 | 47000 | 53000
Analytics-Preparation | 0 | 0 | 58000 | 55000 | 61000

## ProjectProgress
Work Package | Expected Completion % | Completion Lower Limit | Completion Upper Limit | Actual Cost
Tanks-Preparation | 40 | 30 | 60 | 24300
Skids-Preparation | 100 | 100 | 100 | 10125
Civil-Preparation | 70 | 50 | 90 | 28350
Automation-Preparation | 10 | 0 | 40 | 5175
Analytics-Preparation | 20 | 10 | 30 | 9675

## ProjectSchedule
Work Package | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16
Tanks-Preparation | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0 | 0 | 0 | 0 | 0
Skids-Preparation | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Civil-Preparation | 0 | 0 | 0.33 | 0.33 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Automation-Preparation | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
Analytics-Preparation | 0 | 0 | 0 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0 | 0